## Winsford closed projects
Project Planned Hours vrs Actual Recorded hours
[5 empty] | Units | Day or Hours
[9 empty] | Monday |  |  | Sunday
[5 empty] | Date range extracted |  |  | From: | e.g 18/3/19 |  | To : | e.g 24/3/19
[5 empty] | Sites | Select from a list, or leave blank for all sites
Project Id | Project Name | Site | Activity |  | Assigned person | Planned Dates | [6 empty] | Total Planned that week | Total Planned all weeks | Planned work remaining | Over-under quantity from planned | Actual Dates | [6 empty] | Total Actual that week | Total Actual recorded
[6 empty] | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |  |  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
[6 empty] | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 |  |  |  |  | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24
15 | IMI - Write Request for Information/proposal | all | 20 | Map out existing reports | e.g Beverley Hartland | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 5 | 3 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2
15 | IMI - Write Request for Information/proposal | all | 20 | Map out existing reports | e.g Peter Thompson | 0 | 0 | 1 | 0.5 | 1 | 0 | 0 | 2.5 | 9 | 7.5 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2.5
15 | IMI - Write Request for Information/proposal | all | 20 | Map out existing reports | e.g Stephen Gresty | 0 | 0 | 1 | 0.5 | 1 | 0 | 0 | 2.5 | 9 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 8
15 | IMI - Qualtity management tool | all | 22 | Arrange demo | e.g Peter Thompson | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
16 | Feasibility study for capacity planning | Winsford | 25 | Evaluate options for uploading a forecast | e.g Peter Thompson | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
16 | Feasibility study for capacity planning | Winsford | 25 | Evaluate options for uploading a forecast | e.g Peter Kirby - Total E | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Feasibility study for capacity planning | Winsford | 26 | Arrange for user testigng - set up profiles etc | e.g Peter Thompson | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Tuesday = [Actual Dates]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1
Saturday = [Friday]+1
Sunday = [Saturday]+1