## Winsford closed projects
| Project | Project Id # | 15 | Name of project |  | IMI - Qualtity management tool
|  | Units | Day or Hours
[6 empty] | Monday |  |  | Sunday
|  | Date range extracted |  |  | From: | e.g 18/3/19 |  | To : | e.g 24/3/19
Activity |  | Assigned person | Planned Dates | [6 empty] | Total Planned that week | Total Planned all weeks | Planned work remaining | Over-under quantity from planned | Actual Dates | [6 empty] | Total Actual that week | Total Actual recorded
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |  |  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 |  |  |  |  | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24
20 | Map out existing reports | e.g Beverley Hartland | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 5 | 3 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2
20 | Map out existing reports | e.g Joe Smith | 0 | 0 | 1 | 0.5 | 1 | 0 | 0 | 2.5 | 9 | 7.5 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2.5
20 | Map out existing reports | e.g Joe Smith | 0 | 0 | 1 | 0.5 | 1 | 0 | 0 | 2.5 | 9 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 8
22 | Arrange demo | e.g Peter Thompson | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1
Formulas:
Name of project = [Planned Dates]+1
From: = [Name of project]+1
IMI - Qualtity management tool = [From:]+1
Friday = [IMI - Qualtity management tool]+1
Friday = [Thursday]+1
To : = [Friday]+1
e.g 24/3/19 = [To :]+1
Tuesday = [Actual Dates]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Saturday = [Friday]+1
Sunday = [Saturday]+1