## import_WBS
nom | type d'activité | projet | date de création | activité parente | état | responsable | date de début validée | date de début planifiée | date de fin validée | date de fin planifiée | durée validée | durée planifiée | travail validé | done | doneDate | idle | mode de planification
Optimization Spare Part Study | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 |  | in progress | [11 empty] | 1
ADVANCEVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - ADVANCEVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ADVANCEVALVES | in progress | [11 empty] | 1
SPIR 4404GGDTEZ001CC - DUAL PLATE CHECK VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ADVANCEVALVES | in progress | [5 empty] | 1 | 1 | 6 |  |  |  | 1
Génération Operiom - SPIRR et PR - ADVANCEVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ADVANCEVALVES | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
AEVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - AEVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AEVALVES | in progress | [11 empty] | 1
SPIR 4404GGDTEZ002ED - CRYOGENIC BALL VALVES - 2 INCHES AND ABOVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AEVALVES | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 2 | 2 | 16 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - AEVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AEVALVES | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
AIRPRODUCTS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - AIRPRODUCTS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AIRPRODUCTS | in progress | [11 empty] | 1
SPIR 4404TMDKEZ022LE - MEDIUM AND HIGH PURITY NITROGEN GENERATION PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AIRPRODUCTS | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 4 | 4 | 28 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - AIRPRODUCTS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AIRPRODUCTS | in progress | Aurelien Lartigue |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
ALFALAVAL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - ALFALAVAL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ALFALAVAL | in progress | [11 empty] | 1
SPIR 4404HHDKEZ002NV - INERT GAS GENERATION AND DRYING PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ALFALAVAL | in progress | [5 empty] | 15 | 15 | 120 |  |  |  | 1
SPIR 4404TMDJMI056KQ - GAS TURBINE WHRU | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ALFALAVAL | in progress | [5 empty] | 1 | 1 | 11 |  |  |  | 1
Génération Operiom - SPIRR et PR - ALFALAVAL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ALFALAVAL | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
AMPO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - AMPO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AMPO | in progress | [11 empty] | 1
SPIR 4404TMDIEZ004CD - AUTOMATIC ON/OFF BALL VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AMPO | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 1 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDIEZ004EU - AUTOMATIC ON/OFF GATE VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AMPO | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 5 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDIEZ003LS - AUTOMATIC ON/OFF BALL VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AMPO | in progress | [5 empty] | 10 | 10 | 77 |  |  |  | 1
SPIR 4404GGDLEZ002DZ - GATE GLOBE AND CHECK VALVES - 2 INCHES AND ABOVE - STAINLESS STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AMPO | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 8 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDLEZ002EA - GATE GLOBE AND CHECK VALVES - 2 INCHES AND ABOVE - CRYOGENIC SERVICE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AMPO | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 7 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDLEZ002DT - GATE GLOBE AND CHECK VALVES - 2 INCHES AND ABOVE - CARBON STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AMPO | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 5 |  |  |  | 1
Génération Operiom - SPIRR et PR - AMPO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AMPO | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
APCI | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - APCI | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | APCI | in progress | [11 empty] | 1
SPIR 4404TMDVEZ001AD - SPIR TM3700HY001-TM3700HY002 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - APCI | in progress | [5 empty] | 1 | 1 | 1 |  |  |  | 1
Génération Operiom - SPIRR et PR - APCI | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | APCI | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
ATLASCOPCO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - ATLASCOPCO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ATLASCOPCO | in progress | [11 empty] | 1
SPIR 4404HHDKEZ001NH - AIR COMPRESSOR PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ATLASCOPCO | in progress | [5 empty] | 3 | 3 | 21 |  |  |  | 1
Génération Operiom - SPIRR et PR - ATLASCOPCO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ATLASCOPCO | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
AZCUE PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - AZCUE PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AZCUE PUMPS | in progress | [11 empty] | 1
SPIR 4404HHDMEZ002OA - PUMPS IN MACHINERY SPACE - ROTARY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - AZCUE PUMPS | in progress | [5 empty] | 3 | 3 | 24 |  |  |  | 1
Génération Operiom - SPIRR et PR - AZCUE PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | AZCUE PUMPS | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
BADAHEAVYINDUSTRIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - BADAHEAVYINDUSTRIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BADAHEAVYINDUSTRIES | in progress | [11 empty] | 1
SPIR 4404HHDGQS001NN - CRANE FOR ESSENTIAL DIESEL ENGINE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BADAHEAVYINDUSTRIES | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 2 | 2 | 14 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDGQS001UF - MATERIAL HANDLING DEVICES FOR HULL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BADAHEAVYINDUSTRIES | in progress | [5 empty] | 1 | 1 | 2 |  |  |  | 1
Génération Operiom - SPIRR et PR - BADAHEAVYINDUSTRIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BADAHEAVYINDUSTRIES | in progress | Thierry Bastianelli |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
BARTEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - BARTEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BARTEC | in progress | [11 empty] | 1
SPIR 4404HHDEEZ001RD - LIGHTING AND SMALL POWER DISTRIBUTION PANEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BARTEC | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 2 | 2 | 13 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDEEZ001RD - LIGHTING AND SMALL POWER DISTRIBUTION PANEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BARTEC | in progress | [5 empty] | 4 | 4 | 28 |  |  |  | 1
Génération Operiom - SPIRR et PR - BARTEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BARTEC | in progress | Frederic Salles |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
BAYARDSALUMINIUMCONSTRUCTIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - BAYARDSALUMINIUMCONSTRUCTIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BAYARDSALUMINIUMCONSTRUCTIES | in progress | [11 empty] | 1
SPIR 4404LQDKEZ002VF - HELIDECK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BAYARDSALUMINIUMCONSTRUCTIES | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 5 | 5 | 39 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - BAYARDSALUMINIUMCONSTRUCTIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BAYARDSALUMINIUMCONSTRUCTIES | in progress | Thierry Bastianelli | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
BHGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - BHGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BHGE | in progress | [11 empty] | 1
SPIR 4404TMDKEZ540KA - TURBO GENERATORS (KA) - COMMON DF AND SG | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BHGE | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 87 | 87 | 694 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDMEZ175AA - COMMON MR1 AND MR2 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BHGE | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 87 | 87 | 696 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDWMI058AC - BOG TM3721KA001 - TM3722KA001 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BHGE | in progress | [5 empty] | 22 | 22 | 172 |  |  |  | 1
SPIR 4404TMDWMI058AB - BOOSTER TM3600KA001 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BHGE | in progress | [5 empty] | 8 | 8 | 65 |  |  |  | 1
SPIR 4404TMDKEA096BD - FEED GAS COMPANDERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BHGE | in progress | [5 empty] | 3 | 3 | 23 |  |  |  | 1
Génération Operiom - SPIRR et PR - BHGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BHGE | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
BOUSTEAD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - BOUSTEAD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BOUSTEAD | in progress | [11 empty] | 1
SPIR 4404TMDKEZ021LF - DEOILING, CHEMICAL AND ANTIFOAM INJECTION PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BOUSTEAD | in progress | [5 empty] | 7 | 7 | 58 |  |  |  | 1
Génération Operiom - SPIRR et PR - BOUSTEAD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | BOUSTEAD | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
CAMERONSOLUTIONSSDN,BHD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - CAMERONSOLUTIONSSDN,BHD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | CAMERONSOLUTIONSSDN,BHD | in progress | [11 empty] | 1
SPIR V-215A-102-A-0803B - MEG REGENERATION PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - CAMERONSOLUTIONSSDN,BHD | in progress | [5 empty] | 15 | 15 | 119 |  |  |  | 1
Génération Operiom - SPIRR et PR - CAMERONSOLUTIONSSDN,BHD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | CAMERONSOLUTIONSSDN,BHD | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
DAEYANG | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - DAEYANG | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DAEYANG | in progress | [11 empty] | 1
SPIR 4404GGDEEZ002RG - LIGHTING SWITCH SOCKET AND JUNCTION BOX | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DAEYANG | in progress | [5 empty] | 211 | 211 | 1684 |  |  |  | 1
Génération Operiom - SPIRR et PR - DAEYANG | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DAEYANG | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
DEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - DEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DEC | in progress | [11 empty] | 1
SPIR 4404TTDKEZ009EM - PEDESTAL CRANE TT6300YA001 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DEC | in progress | [5 empty] | 13 | 13 | 104 |  |  |  | 1
SPIR 4404TTDKEZ009EM - PEDESTAL CRANE - TT6300YA001 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NATIONALOIL | in progress | [5 empty] | 13 | 13 | 104 |  |  |  | 1
Génération Operiom - SPIRR et PR - DEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DEC | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
DELITEK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - DELITEK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DELITEK | in progress | [11 empty] | 1
SPIR 4404LQDMEZ001VH - WASTE HANDLING EQUIPMENT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DELITEK | in progress | [5 empty] | 1 | 1 | 11 |  |  |  | 1
Génération Operiom - SPIRR et PR - DELITEK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DELITEK | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
DIPIETRO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - DIPIETRO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DIPIETRO | in progress | [11 empty] | 1
SPIR 4404GGDKEA009MN - LABORATORY EQUIPMENT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DIPIETRO | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 2 | 2 | 20 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ002FG - SAMPLE SYSTEMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DIPIETRO | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 3 | 3 | 23 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - DIPIETRO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DIPIETRO | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
D-KTCFLUIDCONTROL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - D-KTCFLUIDCONTROL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | D-KTCFLUIDCONTROL | in progress | [11 empty] | 1
SPIR 4404GGDTEA001BT - STRAINERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - D-KTCFLUIDCONTROL | in progress | [5 empty] | 3 | 3 | 24 |  |  |  | 1
Génération Operiom - SPIRR et PR - D-KTCFLUIDCONTROL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | D-KTCFLUIDCONTROL | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
DONGAVALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - DONGAVALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DONGAVALVE | in progress | [11 empty] | 1
SPIR 4404HHDTEZ001QM - JIS GATE, GLOBE, AND CHECK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DONGAVALVE | in progress | [5 empty] | 1 | 1 | 1 |  |  |  | 1
SPIR 4404HHDTEZ001QK - JIS BALL VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DONGAVALVE | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 11 |  |  |  | 1
Génération Operiom - SPIRR et PR - DONGAVALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DONGAVALVE | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
DONGHWA ENTEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - DONGHWA ENTEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DONGHWA ENTEC | in progress | [11 empty] | 1
SPIR 4404HHDKEZ001OG - WASHING HEATER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DONGHWA ENTEC | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 6 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ002NT - GLYCOL WATER HEATERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DONGHWA ENTEC | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 7 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ003NG - STARTING AIR COMPRESSOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DONGHWA ENTEC | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 5 | 5 | 37 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - DONGHWA ENTEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DONGHWA ENTEC | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
DRAGER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - DRAGER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DRAGER | in progress | [11 empty] | 1
SPIR 4404TMDFEA003DQ - SAFETY EQUIPMENT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - DRAGER | in progress | [5 empty] | 14 | 14 | 111 |  |  |  | 1
Génération Operiom - SPIRR et PR - DRAGER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | DRAGER | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
EATON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - EATON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EATON | in progress | [11 empty] | 1
SPIR 4404TMDEEZ500RI - TOPSIDE LIGHTING FIXTURE, SWITCH AND SOCKET | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EATON | in progress | [5 empty] | 436 | 436 | 3488 |  |  |  | 1
Génération Operiom - SPIRR et PR - EATON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EATON | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
EBARA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - EBARA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EBARA | in progress | [11 empty] | 1
SPIR 4404TMDVEZ002BE - LNG LIQUID TURBINE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EBARA | in progress | [5 empty] | 1 | 1 | 6 |  |  |  | 1
Génération Operiom - SPIRR et PR - EBARA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EBARA | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
EMERSON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - EMERSON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EMERSON | in progress | [11 empty] | 1
SPIR 4404GGDIEZ003DB - ON-LINE ANALYZER AND ANALYZER SHELTER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 13 | 13 | 101 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDIEZ001SL - ON/OFF BUTTERFLY VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 8 | 8 | 63 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ002CA - CONTROL VALVES & SEVERE SERVICE CONTROL VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 9 | 9 | 70 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDTEZ001QA - BUTTERFLY VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 0 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ003BY - CENTRAL CONTROL ROOM OPERATOR CONSOLE FURNITURE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 11 | 11 | 90 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TTDIEM002DE - CONDENSATE METERING | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | [5 empty] | 5 | 5 | 36 |  |  |  | 1
SPIR 4404TMDIEZ003LT - AUTOMATIC ON/OFF BUTTERFLY VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 4 | 4 | 29 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ002CQ - ELECTROMAGNETIC FLOWMETERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 3 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDIEZ002FI - VORTEX FLOW METERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 14 | 14 | 112 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEA031CT - RADAR LEVEL TRANSMITTER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 47 | 47 | 373 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEA031CX - TEMPERATURE TRANSMITTERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 14 | 14 | 109 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ032CW - PRESSURE AND DIFFERENTIAL PRESSURE TRANSMITTERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 14 | 14 | 114 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDIEZ001SG - TANK LEVEL GAUGING SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 6 | 6 | 49 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ019DC - FIRE AND GAS DETECTORS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 62 | 62 | 494 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDIEZ001QX - RESTRICTION ORIFICE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 11 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ006AG - ICSS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 5 | 5 | 38 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDIEZ001SO - CONTROL VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | [5 empty] | 5 | 5 | 40 |  |  |  | 1
SPIR 4404TMDIEZ004CE - AUTOMATIC ON/OFF BUTTERFLY VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | [5 empty] | 4 | 4 | 29 |  |  |  | 1
SPIR 4404TMDGEZ023LR - HIPPS (LR) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EMERSON | in progress | [5 empty] | 1 | 1 | 2 |  |  |  | 1
Génération Operiom - SPIRR et PR - EMERSON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EMERSON | in progress | Aurelien Lartigue |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
ENDRESSHAUSER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - ENDRESSHAUSER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ENDRESSHAUSER | in progress | [11 empty] | 1
SPIR 4404HHDIEZ001SR - FLOWMETER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ENDRESSHAUSER | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 3 | 3 | 27 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDIEZ001SJ - INSTRUMENT(PT TT LT) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ENDRESSHAUSER | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 27 | 27 | 215 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - ENDRESSHAUSER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ENDRESSHAUSER | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
EVACOY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - EVACOY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EVACOY | in progress | [11 empty] | 1
SPIR 4404HHDVEZ002NL - SEWAGE TREATMENT PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EVACOY | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 5 | 5 | 38 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - EVACOY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EVACOY | in progress | Frederic Salles | 2020-06-10 | 2020-06-10 | 2020-06-11 | 2020-06-11 | 1 | 1 | 8 |  |  |  | 1
EXCELLIFT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - EXCELLIFT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EXCELLIFT | in progress | [11 empty] | 1
SPIR 4404TMDVEZ003EN - LIFTING AND HANDLING DEVICES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - EXCELLIFT | in progress | Thierry Bastianelli | 2020-06-09 | 2020-06-09 | 2020-06-14 | 2020-06-14 | 5 | 5 | 44 |  |  |  | 1
Génération Operiom - SPIRR et PR - EXCELLIFT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | EXCELLIFT | in progress | Thierry Bastianelli | 2020-06-14 | 2020-06-14 | 2020-06-15 | 2020-06-15 | 1 | 1 | 8 |  |  |  | 1
FEB | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - FEB | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FEB | in progress | [11 empty] | 1
SPIR 4404TTDKEZ009KP - PEDESTAL CRANES (KP) - TT6300YA003 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - FEB | in progress | [5 empty] | 14 | 14 | 110 |  |  |  | 1
Génération Operiom - SPIRR et PR - FEB | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FEB | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
FIRENOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - FIRENOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FIRENOR | in progress | [11 empty] | 1
SPIR 4404HHDKEZ001UC - LOOSE LIFE SAVING EQUIPMENTS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - FIRENOR | in progress | [5 empty] | 2 | 2 | 19 |  |  |  | 1
Génération Operiom - SPIRR et PR - FIRENOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FIRENOR | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
FLEXIFRANCE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - FLEXIFRANCE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FLEXIFRANCE | in progress | [11 empty] | 1
SPIR 4404YYDURX001IA - AVGM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - FLEXIFRANCE | in progress | [5 empty] | 1 | 1 | 1 |  |  |  | 1
Génération Operiom - SPIRR et PR - FLEXIFRANCE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FLEXIFRANCE | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
FMCTECHNOLOGIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - FMCTECHNOLOGIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FMCTECHNOLOGIES | in progress | [11 empty] | 1
SPIR 4404TTDVEZ059EL - MARINE LOADING ARMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - FMCTECHNOLOGIES | in progress | [5 empty] | 18 | 18 | 146 |  |  |  | 1
Génération Operiom - SPIRR et PR - FMCTECHNOLOGIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FMCTECHNOLOGIES | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
FRAMO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - FRAMO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FRAMO | in progress | [11 empty] | 1
SPIR 4404HHDMEZ005AL - SEAWATER LIFT PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - FRAMO | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 6 | 6 | 44 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDMEZ003NX - HYDRAULIC DRIVEN PUMP | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - FRAMO | in progress | [5 empty] | 7 | 7 | 57 |  |  |  | 1
SPIR 4404HHDMEZ191KW - CENTRIFUGAL PUMP | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - FRAMO | in progress | [5 empty] | 2 | 2 | 13 |  |  |  | 1
Génération Operiom - SPIRR et PR - FRAMO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | FRAMO | in progress | Thierry Bastianelli |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
GEA WESTFALIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - GEA WESTFALIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | GEA WESTFALIA | in progress | [11 empty] | 1
SPIR 4404HHDKEZ002NK - SLOP WATER TREATMENT PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BHGE | in progress | [5 empty] | 4 | 4 | 31 |  |  |  | 1
SPIR 4404HHDKEZ003NJ - DIESEL OIL & LUBE OIL PURIFIER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - BHGE | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 8 | 8 | 62 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - GEA WESTFALIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | GESENSING | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
GESENSING | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - GESENSING | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | GESENSING | in progress | [11 empty] | 1
SPIR 4404GGDIEZ003CS - ULTRASONIC FLOWMETER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - GESENSING | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 5 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDIEZ001CS - ULTRASONIC FLOW METERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - GESENSING | in progress | [5 empty] | 1 | 1 | 6 |  |  |  | 1
Génération Operiom - SPIRR et PR - GESENSING | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | GESENSING | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
HANWHAPOWERSYSTEMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - HANWHAPOWERSYSTEMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HANWHAPOWERSYSTEMS | in progress | [11 empty] | 1
SPIR 4404TTDKEZ003OC - WARM UP COMPRESSOR AND WARM UP HEATER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HANWHAPOWERSYSTEMS | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 3 | 3 | 22 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ002NF - AIR COMPRESSOR PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HANWHAPOWERSYSTEMS | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 14 | 14 | 110 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - HANWHAPOWERSYSTEMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HANWHAPOWERSYSTEMS | in progress | Thierry Bastianelli | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
HIAIRKOREA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - HIAIRKOREA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HIAIRKOREA | in progress | [11 empty] | 1
SPIR 4404TMDKEZ003MM - HVAC - TECHNICAL BUILDING S07 UIR AND LABORATORY (MM) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HIAIRKOREA | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 24 | 24 | 196 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDKEZ104DS - HVAC BUILDINGS P02 AND S04 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HIAIRKOREA | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 26 | 26 | 207 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ004VA - HULL & LQ HVAC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HIAIRKOREA | in progress | [5 empty] | 284 | 284 | 2271 |  |  |  | 1
Génération Operiom - SPIRR et PR - HIAIRKOREA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HIAIRKOREA | in progress | Frederic Salles |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
HWASEUNGEXWILLCOLTD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - HWASEUNGEXWILLCOLTD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HWASEUNGEXWILLCOLTD | in progress | [11 empty] | 1
SPIR 4404HHDMEZ001ON - FENDER AND FENDER HANDLING DAVIT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HWASEUNGEXWILLCOLTD | in progress | Frederic Salles | 2020-06-09 | 2020-06-09 | 2020-06-19 | 2020-06-19 | 11 | 11 | 86 |  |  |  | 1
Génération Operiom - SPIRR et PR - HWASEUNGEXWILLCOLTD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HWASEUNGEXWILLCOLTD | in progress | Frederic Salles | 2020-06-19 | 2020-06-19 | 2020-06-20 | 2020-06-20 | 1 | 1 | 8 |  |  |  | 1
HYLOK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - HYLOK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HYLOK | in progress | [11 empty] | 1
SPIR 4404HHDTEZ005QD - CRYOGENIC MODULAR BALL VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HYLOK | in progress | Frederic Salles | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-05-07 | 1 | 1 | 5 |  |  |  | 1
SPIR 4404HHDTEZ001QD - CRYOGENIC BALL VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HYLOK | in progress | Frederic Salles | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-05-07 | 1 | 1 | 5 |  |  |  | 1
SPIR 4404GGDTEZ001PM - NON-CRYOGENIC BALL VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HYLOK | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 1 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDIEZ001SM - ON/OFF BALL VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HYLOK | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 2 | 2 | 13 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDTEZ002PM - NON-CRYOGENIC BALL VALVE FOR MODULAR BALL VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - HYLOK | in progress | Frederic Salles | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-05-07 | 1 | 1 | 1 |  |  |  | 1
Génération Operiom - SPIRR et PR - HYLOK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | HYLOK | in progress | Frederic Salles | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
ICARUS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - ICARUS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ICARUS | in progress | [11 empty] | 1
SPIR 4404GGDTEA002FP - SPECIAL CHECK VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ICARUS | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 4 |  |  |  | 1
SPIR 4404GGDTEA002BB - CRYOGENIC DUAL PLATE CHECK VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ICARUS | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 1 |  |  |  | 1
Génération Operiom - SPIRR et PR - ICARUS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ICARUS | in progress |  | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
IHCSASB.V. | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - IHCSASB.V. | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | IHCSASB.V. | in progress | [11 empty] | 1
SPIR 4404HHDKEZ003OU - CONDENSATE OFFLOADING PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - IHCSASB.V. | in progress | [5 empty] | 7 | 7 | 57 |  |  |  | 1
Génération Operiom - SPIRR et PR - IHCSASB.V. | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | IHCSASB.V. | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
IMENCO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - IMENCO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | IMENCO | in progress | [11 empty] | 1
SPIR 4404HHDMEZ089OQ - HELICOPTER REFUEL SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - IMENCO | in progress | [5 empty] | 1 | 1 | 11 |  |  |  | 1
Génération Operiom - SPIRR et PR - IMENCO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | IMENCO | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
IMIORTON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - IMIORTON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | IMIORTON | in progress | [11 empty] | 1
SPIR 4404GGDTEZ002DX - BUTTERFLY VALVES CONCENTRIC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - IMIORTON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 2 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDIEZ002EW - MOTOR OPERATING VALVES MOV | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - IMIORTON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 4 | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDGEZ017LK - DRYER SEQUENCE VALVES (LK) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - IMIORTON | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 6 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - IMIORTON | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | IMIORTON | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
JAN | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - JAN | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | JAN | in progress | [11 empty] | 1
SPIR 4404TTDKEZ008KP - PEDESTAL CRANES (KP) - TT6300YA002 | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JAN | in progress | [5 empty] | 1 | 1 | 2 |  |  |  | 1
Génération Operiom - SPIRR et PR - JAN | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | JAN | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
JEITEK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - JEITEK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | JEITEK | in progress | [11 empty] | 1
SPIR 4404LQDIEZ001SH - AIR LOCK ALARM SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JEITEK | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 4 | 4 | 29 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - JEITEK | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | JEITEK | in progress |  | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
JOHNSONCONTROLS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - JOHNSONCONTROLS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | JOHNSONCONTROLS | in progress | [11 empty] | 1
SPIR 4404HHDKEZ002NR - HX FOAM PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JOHNSONCONTROLS | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 8 | 8 | 62 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ001OV - SAFETY SHOWERS AND EYEWASHES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JOHNSONCONTROLS | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 3 | 3 | 27 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ001OK - WATER MIST SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JOHNSONCONTROLS | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 4 | 4 | 33 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ003NO - DRY CHEMICAL POWDER PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JOHNSONCONTROLS | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 6 | 6 | 46 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ002NP - FIXED GASEOUS EXTINGUISHING SYSTEM (NP) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JOHNSONCONTROLS | in progress | Thierry Bastianelli | 2020-06-09 | 2020-06-09 | 2020-07-08 | 2020-07-08 | 29 | 29 | 233 |  |  |  | 1
SPIR 4404TMDWPV096KR - CO2 THERMAL INCINERATOR PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JOHNSONCONTROLS | in progress | [5 empty] | 1 | 1 | 4 |  |  |  | 1
SPIR 4404HHDKEZ001UD - LOOSE FIRE FIGHTING EQUIPMENTS FOR TWOYEARS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - JOHNSONCONTROLS | in progress | [5 empty] | 1 | 1 | 2 |  |  |  | 1
Génération Operiom - SPIRR et PR - JOHNSONCONTROLS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | JOHNSONCONTROLS | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
KOCH-GLITSCH | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - KOCH-GLITSCH | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | KOCH-GLITSCH | in progress | [11 empty] | 1
SPIR 4404TMDVEZ701KH - TRAYS AND INTERNALS IN HOT SECTION | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - KOCH-GLITSCH | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 |  |  |  | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDKEJ00572 - COLUMN INTERNALS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - KOCH-GLITSCH | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 |  |  |  | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDKEJ00573 - DRUM INTERNALS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - KOCH-GLITSCH | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 |  |  |  | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - KOCH-GLITSCH | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | KOCH-GLITSCH | in progress | Thierry Bastianelli | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
KONGSBERGMARITIME | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - KONGSBERGMARITIME | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | KONGSBERGMARITIME | in progress | [11 empty] | 1
SPIR 4404HHDIEZ001SD - HEADING CONTROL SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - KONGSBERGMARITIME | in progress | [5 empty] | 1 | 1 | 1 |  |  |  | 1
Génération Operiom - SPIRR et PR - KONGSBERGMARITIME | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | KONGSBERGMARITIME | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
KSBSAS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - KSBSAS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | KSBSAS | in progress | [11 empty] | 1
SPIR 4404HHDIEZ001SK - ON/OFF BUTTERFLY VALVES FOR CRYOGENIC SERVICE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - KSBSAS | in progress | [5 empty] | 9 | 9 | 73 |  |  |  | 1
SPIR 4404HHDTEZ001QE - CRYOGENIC BUTTERFLY VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - KSBSAS | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 5 | 5 | 40 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - KSBSAS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | KSBSAS | in progress | Aurelien Lartigue |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
MOKVELD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - MOKVELD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | MOKVELD | in progress | [11 empty] | 1
SPIR 4404GGDTEZ012BF - MOKVELD - NON-SLAM CHECKVALVES AXIAL TYPE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - MOKVELD | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 6 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - MOKVELD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | MOKVELD | in progress | Aurelien Lartigue |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
NATIONALOIL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NATIONALOIL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NATIONALOIL | in progress | [11 empty] | 1
SPIR 4404HHDKEZ001NM - CRANE FOR THRUSTERS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NATIONALOIL | in progress | [5 empty] | 2 | 2 | 14 |  |  |  | 1
Génération Operiom - SPIRR et PR - NATIONALOIL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NATIONALOIL | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
NEUMANN&ESSER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NEUMANN&ESSER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NEUMANN&ESSER | in progress | [11 empty] | 1
SPIR 4404TMDMEZ706KY - OFF GAS COMPRESSOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NEUMANN&ESSER | in progress | [5 empty] | 9 | 9 | 68 |  |  |  | 1
Génération Operiom - SPIRR et PR - NEUMANN&ESSER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NEUMANN&ESSER | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
NEWAY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NEWAY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NEWAY | in progress | [11 empty] | 1
SPIR 4404GGDLEV004EB - BALL VALVES-2 INCHES AND ABOVE RATING UP TO 600 LBS - STAINLESS STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NEWAY | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 0 |  |  |  | 1
SPIR 4404GGDLEV004DV - BALL VALVES-2 INCHES AND ABOVE RATING UP TO 600 LBS - CARBON STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NEWAY | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 0 |  |  |  | 1
Génération Operiom - SPIRR et PR - NEWAY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NEWAY | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
NIKKISO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NIKKISO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NIKKISO | in progress | [11 empty] | 1
SPIR 4404GGDMEZ001BC - CRYOGENIC PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NIKKISO | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 10 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ003NY - LNG CARGO PUMPS AND SPRAY PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NIKKISO | in progress | [5 empty] | 3 | 3 | 24 |  |  |  | 1
Génération Operiom - SPIRR et PR - NIKKISO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NIKKISO | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
NOKIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NOKIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NOKIA | in progress | [11 empty] | 1
SPIR 4404GGDCEZ004ES - MAIN TELECOM CONTRACTOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NOKIA | in progress | [5 empty] | 236 | 236 | 1888 |  |  |  | 1
SPIR 4404GGDCEZ004SA - MAIN TELECOM CONTRACTOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NOKIA | in progress | [5 empty] | 129 | 129 | 1031 |  |  |  | 1
Génération Operiom - SPIRR et PR - NOKIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NOKIA | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
NORSAFE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NORSAFE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NORSAFE | in progress | [11 empty] | 1
SPIR 4404HHDMEZ003NB - FAST RESCUE CRAFT & DAVIT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NORSAFE | in progress | [5 empty] | 2 | 2 | 20 |  |  |  | 1
SPIR 4404LQDMEZ002NA - LIFEBOAT AND DAVIT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NORSAFE | in progress | [5 empty] | 19 | 19 | 148 |  |  |  | 1
Génération Operiom - SPIRR et PR - NORSAFE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NORSAFE | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
NOV | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NOV | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NOV | in progress | [11 empty] | 1
SPIR 4404TMDKEZ011LA - DESANDING PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NOV | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
Génération Operiom - SPIRR et PR - NOV | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NOV | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
NVENT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - NVENT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NVENT | in progress | [11 empty] | 1
SPIR 4404GGDEEZ002RJ - ELECTRICAL HEAT TRACING | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - NVENT | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 9 | 9 | 74 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - NVENT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | NVENT | in progress | Frederic Salles | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
OMBVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - OMBVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | OMBVALVES | in progress | [11 empty] | 1
SPIR 4404GGDTEY001EY - BUTTERFLY VALVES- DOUBLE OR TRIPLE OFFSET – STAINLESS STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - OMBVALVES | in progress | [5 empty] | 1 | 1 | 10 |  |  |  | 1
SPIR 4404GGDTFA001FA - BUTTERFLY VALVES - CUPRO-NICKEL ALLOY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - OMBVALVES | in progress | [5 empty] | 2 | 2 | 14 |  |  |  | 1
SPIR 4404GGDTEX001EZ - CRYOGENIC BUTTERFLY VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - OMBVALVES | in progress | [5 empty] | 4 | 4 | 35 |  |  |  | 1
SPIR 4404GGDTEX001EX - BUTTERFLY VALVES- DOUBLE OR TRIPLE OFFSET – CARBON STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - OMBVALVES | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-21 | 2020-06-21 | 13 | 13 | 102 |  |  |  | 1
Génération Operiom - SPIRR et PR - OMBVALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | OMBVALVES | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
ORGA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - ORGA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ORGA | in progress | [11 empty] | 1
SPIR 4404LQDEEZ002RA - NAVIGATION AIDS SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - ORGA | in progress | [5 empty] | 1 | 1 | 5 |  |  |  | 1
Génération Operiom - SPIRR et PR - ORGA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | ORGA | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
PERONIPOMPE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - PERONIPOMPE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | PERONIPOMPE | in progress | [11 empty] | 1
SPIR 4404TMDMEJ700KU - API 674 POSITIVE DISPLACEMENT PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - PERONIPOMPE | in progress | [5 empty] | 2 | 2 | 19 |  |  |  | 1
Génération Operiom - SPIRR et PR - PERONIPOMPE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | PERONIPOMPE | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
PKVALVLE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - PKVALVLE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | PKVALVLE | in progress | [11 empty] | 1
SPIR 4404HHDIEF001SN - ON/OFF GATE VALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - PKVALVE | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 1 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDTEF001QB - GLOBE, GATE AND CHECK VALVES DN 50 AND ABOVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - PKVALVE | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 4 |  |  |  | 1
SPIR 4404HHDTEZ003WE - MANULA HYDRAULIC REMOTE CONTROL DEVICE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - PKVALVE | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 2 |  |  |  | 1
Génération Operiom - SPIRR et PR - PKVALVE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | PKVALVE | in progress |  | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
RMT(VALVOMECCANICA) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - RMT(VALVOMECCANICA) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | RMT(VALVOMECCANICA) | in progress | [11 empty] | 1
SPIR 4404GGDTEA003FC - BALL VALVES-2ANDABOVE-900 LBS AND ABOVE-CARBON STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - RMT(VALVOMECCANICA) | in progress | [5 empty] | 1 | 1 | 4 |  |  |  | 1
SPIR 4404GGDTEA003EC - 2 INCHES AND ABOVE - 900 LBS AND ABOVE - STAINLESS STEEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - RMT(VALVOMECCANICA) | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 1 | 1 | 2 |  |  |  | 1
Génération Operiom - SPIRR et PR - RMT(VALVOMECCANICA) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | RMT(VALVOMECCANICA) | in progress | Aurelien Lartigue |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
SAMKUNCENTURYCOLTD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SAMKUNCENTURYCOLTD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SAMKUNCENTURYCOLTD | in progress | [11 empty] | 1
SPIR 4404HHDKEZ005OE - FRESH WATER TREATMENT PACKAGES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SAMKUNCENTURYCOLTD | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 3 | 3 | 24 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ002OX - CHEMICAL DOSING UNIT | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SAMKUNCENTURYCOLTD | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 2 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - SAMKUNCENTURYCOLTD | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SAMKUNCENTURYCOLTD | in progress | Thierry Bastianelli | 2020-06-09 | 2020-06-09 | 2020-06-10 | 2020-06-10 | 1 | 1 | 8 |  |  |  | 1
SATOMAS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SATOMAS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SATOMAS | in progress | [11 empty] | 1
SPIR 4404HHDKEZ003OJ - EMERGENCY DIESEL GENERATOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SATOMAS | in progress | [5 empty] | 6 | 6 | 48 |  |  |  | 1
Génération Operiom - SPIRR et PR - SATOMAS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SATOMAS | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SCHLUMBERGER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SCHLUMBERGER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SCHLUMBERGER | in progress | [11 empty] | 1
SPIR 4404TMDVEZ005KB - MEG REGENERATION PACKAGE (KB) | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SCHLUMBERGER | in progress | [5 empty] | 11 | 11 | 91 |  |  |  | 1
Génération Operiom - SPIRR et PR - SCHLUMBERGER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SCHLUMBERGER | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SCHNEIDERELECTRIC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SCHNEIDERELECTRIC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SCHNEIDERELECTRIC | in progress | [11 empty] | 1
SPIR 4404HHDEEZ002DH - HV SWITCHGEARS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SCHNEIDERELECTRIC | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 4 | 4 | 36 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDEEA005EV - ECS AND PMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SCHNEIDERELECTRIC | in progress | [5 empty] | 1 | 1 | 7 |  |  |  | 1
SPIR 4404HHDECA101DI - LV SWITCHGEARS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SCHNEIDERELECTRIC | in progress | [5 empty] | 24 | 24 | 192 |  |  |  | 1
Génération Operiom - SPIRR et PR - SCHNEIDERELECTRIC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SCHNEIDERELECTRIC | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SEKO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SEKO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SEKO | in progress | [11 empty] | 1
SPIR 4404TMDMEZ709KV - API 675 POSITIVE DISPLACEMENT PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SEKO | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
Génération Operiom - SPIRR et PR - SEKO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SEKO | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SEMCOMARITIME | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SEMCOMARITIME | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SEMCOMARITIME | in progress | [11 empty] | 1
SPIR 4404GGDBEZ001CH - DELUGE VALVES AND SKIDS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SEMCOMARITIME | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 19 | 19 | 151 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ002NQ - LX FOAM PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SEMCOMARITIME | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 10 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDKEZ002OR - HELICOPTER REFUEL UNIT FIRE FIGHTING PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SEMCOMARITIME | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 7 | 1 | 2020-06-09 | 1 | 1
SPIR 4404HHDTEZ001QQ - HYDRANT WITH HOSE CABINET AND HOSE REEL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SEMCOMARITIME | in progress | [5 empty] | 7 | 7 | 59 |  |  |  | 1
Génération Operiom - SPIRR et PR - SEMCOMARITIME | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SEMCOMARITIME | in progress | Aurelien Lartigue |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
SESPI | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SESPI | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SESPI | in progress | [11 empty] | 1
SPIR 4404TMDVEZ004EQ - ELECTROCHLORINATION PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SESPI | in progress | [5 empty] | 4 | 4 | 36 |  |  |  | 1
Génération Operiom - SPIRR et PR - SESPI | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SESPI | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SIEMENS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SIEMENS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SIEMENS | in progress | [11 empty] | 1
SPIR 4404HHDEEZ002RC - THRUSTER DRIVE SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SIEMENS | in progress | [5 empty] | 1 | 1 | 4 |  |  |  | 1
Génération Operiom - SPIRR et PR - SIEMENS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SIEMENS | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SOFEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SOFEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SOFEC | in progress | [11 empty] | 1
SPIR 4404UUDKEZ109S9 - TMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SOFEC | in progress | [5 empty] | 50 | 50 | 402 |  |  |  | 1
Génération Operiom - SPIRR et PR - SOFEC | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SOFEC | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
STXENGINE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - STXENGINE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | STXENGINE | in progress | [11 empty] | 1
SPIR 4404HHDKEZ002NE - ESSENTIAL DIESEL GENERATOR ENGINE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - STXENGINE | in progress | [5 empty] | 24 | 24 | 191 |  |  |  | 1
Génération Operiom - SPIRR et PR - STXENGINE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | STXENGINE | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SULZER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SULZER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SULZER | in progress | [11 empty] | 1
SPIR 4404GGDKEJ00571 - MR1 CONDENSER SPRAY | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SULZER | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 |  |  |  | 1 | 2020-06-09 | 1 | 1
SPIR 4404TMDVEZ003KI - BINTERNALSB | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SULZER | in progress | [5 empty] | 1 | 1 | 1 |  |  |  | 1
SPIR 4404HHDKEZ003NS - FIREWATER PUMP PACKAGE & JOCKEY PUMP | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SULZER | in progress | [5 empty] | 9 | 9 | 71 |  |  |  | 1
Génération Operiom - SPIRR et PR - SULZER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SULZER | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
SUNDYNE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - SUNDYNE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SUNDYNE | in progress | [11 empty] | 1
SPIR 4404TMDKEZ003KX - REGENERATION GAS EXCESS COMPRESSOR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - SUNDYNE | in progress | [5 empty] | 5 | 5 | 41 |  |  |  | 1
Génération Operiom - SPIRR et PR - SUNDYNE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | SUNDYNE | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
TRELLEBORG | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - TRELLEBORG | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | TRELLEBORG | in progress | [11 empty] | 1
SPIR 4404HHDYEZ002DR - SEA WATER INTAKE RISERS PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - TRELLEBORG | in progress | [5 empty] | 3 | 3 | 20 |  |  |  | 1
Génération Operiom - SPIRR et PR - TRELLEBORG | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | TRELLEBORG | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
UNIDRO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - UNIDRO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | UNIDRO | in progress | [11 empty] | 1
SPIR 4404HHDKEZ002LC - FRESH WATER GENERATION PACKAGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - UNIDRO | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 13 | 13 | 104 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - UNIDRO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | UNIDRO | in progress | Thierry Bastianelli |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
VALVE ITALIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - VALVE ITALIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | VALVE ITALIA | in progress | [11 empty] | 1
SPIR 4404TMDFEZ003DP - INERGEN SYSTEMS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - VALVE ITALIA | in progress | Thierry Bastianelli | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 14 | 14 | 111 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - VALVE ITALIA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | VALVE ITALIA | in progress | Thierry Bastianelli |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
VERTIV | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - VERTIV | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | VERTIV | in progress | [11 empty] | 1
SPIR 4404GGDEEZ004DN - AC AND DC UPS AND BATTERIES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - VERTIV | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 5 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - VERTIV | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | VERTIV | in progress | Frederic Salles |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
WARTSILA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - WARTSILA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WARTSILA | in progress | [11 empty] | 1
SPIR 4404HHDMEZ002ND - THRUSTER | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WARTSILA | in progress | [5 empty] | 14 | 14 | 113 |  |  |  | 1
SPIR 4404HHDIEZ001SC - LTD MONITORING SYSTEM | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WARTSILA | in progress | [5 empty] | 1 | 1 | 3 |  |  |  | 1
Génération Operiom - SPIRR et PR - WARTSILA | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WARTSILA | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
WEIR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - WEIR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WEIR | in progress | [11 empty] | 1
SPIR 4404GGDIPV004CL - PRESSURE SAFETY VALVES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WEIR | in progress | Aurelien Lartigue | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 14 | 14 | 111 | 1 | 2020-06-09 | 1 | 1
SPIR 4404GGDMEZ710KS - API 610 CENTRIFUGAL PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WEIR | in progress | [5 empty] | 11 | 11 | 89 |  |  |  | 1
SPIR 4404TMDMEZ003BA - CENTRIFUGAL PUMPS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WEIR | in progress | [5 empty] | 14 | 14 | 115 |  |  |  | 1
Génération Operiom - SPIRR et PR - WEIR | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WEIR | in progress | Aurelien Lartigue |  |  |  |  | 1 | 1 | 8 |  |  |  | 1
WIKAINSTRUMENTSSARL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - WIKAINSTRUMENTSSARL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WIKAINSTRUMENTSSARL | in progress | [11 empty] | 1
SPIR 4404GGDIEZ001DA - TEMPERATURE GAUGES AND THERMOWELLS | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WIKAINSTRUMENTSSARL | in progress | [5 empty] | 17 | 17 | 135 |  |  |  | 1
SPIR 4404GGDIEZ001CV - PRESSURE AND DIFFERENTIAL PRESSURE GAUGES | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WIKAINSTRUMENTSSARL | in progress | [5 empty] | 15 | 15 | 119 |  |  |  | 1
SPIR 4404HHDIEZ001QR - MANUAL GAUGE | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WIKAINSTRUMENTSSARL | in progress | Aurelien Lartigue | 2020-06-09 | 2020-06-09 | 2020-06-22 | 2020-06-22 | 13 | 13 | 105 |  |  |  | 1
Génération Operiom - SPIRR et PR - WIKAINSTRUMENTSSARL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WIKAINSTRUMENTSSARL | in progress | [5 empty] | 1 | 1 | 8 |  |  |  | 1
WOOJOO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Optimization Spare Part Study | in progress | [11 empty] | 1
Implémentation Operiom - SPIR - WOOJOO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WOOJOO | in progress | [11 empty] | 1
SPIR 4404HHDIEZ001SI - JUNCTION BOX | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WOOJOO | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 21 | 21 | 167 | 1 | 2020-06-09 | 1 | 1
SPIR 4404LQDIEZ002SF - REFRIGERATION CHAMBER CALL & HOSPITAL CALL | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | Implémentation Operiom - SPIR - WOOJOO | in progress | Frederic Salles | 2020-06-01 | 2020-06-01 | 2020-06-09 | 2020-06-09 | 1 | 1 | 4 | 1 | 2020-06-09 | 1 | 1
Génération Operiom - SPIRR et PR - WOOJOO | Task | PILOTE PURCHASE REQUEST CORAL | 2020-06-09 | WOOJOO | in progress | Frederic Salles |  |  |  |  | 1 | 1 | 8 |  |  |  | 1